## Sayfa1
Start Date 24/10/2023
Week |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Procedural Steps | Current State | 2 October 2023 | 9 October 2023 | 16 October 2023 | 23 October 2023 | 30 October 2023 | 6 November 2023 | 13 November 2023 | 20 November 2023 | 27 November 2023 | 4 December 2023 | 11 December 2023 | 18 December 2023 | 25 December 2023 | 1 January 2024 | 8 January 2024 | 15 January 2024
Team Setup | Completed | bar: 1 to 2
Project Proposal Form | Completed | bar: 2
Project Selection Form | Completed | bar: 2
Project Work Plan | Continuing | bar: 3 to 4
Literature Review | Continuing | bar: 4 to 6
Software Requirements Specification | Continuing | bar: 6 to 9
Project Webpage | Continuing | bar: 10 to 12
Software Design Description | Continuing | bar: 11 to 13
Project Report | Continuing | bar: 14 to 15
Presentation | Continuing | bar: 16